## Slide 1
Technical design aspects to be dealt with at headquarters are the standard parameters for typical work items. These standards encompass ranges of values within which the site engineer is allowed to operate. Design standards normally provide general guidelines relating to the following items:
• Location: Reference to places to be served and major obstacles to be avoided,
such as marshy areas, crops and difficult river crossings.

## Slide 2
• Alignment requirements: Instructions for setting out the course of the road.
• Technical performance: Specifications of maximum gradients, minimum
horisontal and vertical curvature, sight distances, super-elevation, cross-fall, etc.
• Materials requirements: Specification of the type, quality and method of
compaction, curing and tests to be performed.
• Structures: Recommendations on the use of local building materials such as
stone and timber, and on the design of bridges, culverts and road protection
works.
Road location and alignment are of particular importance when applying labourbased
work methods. High alignment standards aiming to reduce the number of
curves and soft gradients would require, particularly in hilly or mountainous terrain,
considerable longitudal earth movements which cannot be carried out economically
by labour.
Therefore, the site engineer should be aware of the need to select an
alignment where earth works are mainly lateral (cut to fill), and where horisontal and
vertical alignments will not lead to any significant longitudal haulage.

## Slide 3
Horisontal and Vertical Alignment
• Maximum grade
• Minimum horisontal radius
• Minimum vertical curvature
• Horisontal sight distance
Materials Data
• Soil or rock type
• Compaction and moisture content
• Curing requirements
• Aggregate gradations
• Mix proportions
• Strength requirements
• Tests to be performed

## Slide 4
Typical Cross Section
• Road width
• Maximum earth side slopes
• Pavement width
• Layer thickness
• Ditch details
• Width cleared of vegetation
Typical Structural Design
• River crossings
• Culverts
• Drifts
• Retaining walls
• Soil protection measures

## Slide 5
The design process as such deals with the following main steps:
• Establish road function.
• Assess the design traffic and its characteristics.
• Assess other factors which should affect the design (terrain, type of sub-grade, sub-grade strength, availability and cost of construction materials, etc.).
• Select geometric design standards (road cross-section, design speed and speed related standards).
• Select appropriate pavement design (total pavement thickness, thickness and type of materials for each component layer).
• Assess the need for road structures (bridges, culverts, retaining walls, etc)
• Assess the availability of labour in the vicinity of the road work sites.
• Assess the availability of local contractors.

## Slide 6
Parameter | Ref. | Class V F R M | Class VI F R M | Class VII F R M | ILO F M
Type of Terrain1 |  |  |  |  | 
Average Daily Traffic (vpd) 100-300 50-100 < 50 < 50 Design Speed (km/h) 60 40 20 60 40 20 40 30 20 30 Formation Width (m) a 7 7 6.5 6.5 6.5 6 6 6 5.5 5.5 5.5 Carriage-way Width (m) b 5.5 3.5 3.5 5.5 Shoulder Width (m) c 0.75 0.75 0.5 1.5 1.5 1.25 1.25 1.25 1.0 0 0 Cross-fall (%) d 3 - 4 8 Max Gradient (%) 7 8 9 7 8 9 8 9 10 10 Max Axle Load (tonnes) 9.1 5 |  |  |  |  | 

## Slide 7
Selecting the most appropriate road alignment is the most important part of any road planning and design process. If the wrong alignment is chosen, it can result in delays to construction works, over-use of resources and a road which is difficult and expensive to maintain.
The types of surveying work commonly demanded of road engineers and technicians are:
• rough topographical surveys preparatory to selecting routes,
• surveys of catchment areas preparatory to designing bridges and culverts,
• soil surveys to check adequacy of subsoils and quarry materials,
• more accurate surveys of the selected site or route to enable quantities of material to be estimated, and
• setting out of the actual works.
When surveying possible alignments for secondary and tertiary roads, it is often sufficient to drive a four-wheel drive vehicle along the proposed routes. The routes can be marked on large-scale maps, and the reading of the vehicle's oedometer can be used as a measure of distance.

## Slide 8
Best Crossing
Point
Intersection
Point
The aim of a topographical survey is to establish the most economical site or route for the proposed works. For a low-cost project such a survey would normally consist of a walk over the area of choice, noting possible alignments or sites, potential quarry sites, and soil conditions. A line level, linen tape and short tape are the minimum requirements for such reconnaissance work.

## Slide 9
The alignment should be selected to avoid areas of bad or difficult drainage, areas of bad soil or large earthworks, areas of rock outcrops or heavy bush clearing. In
addition, where drainage structures are needed, the road alignment should be selected so that the structures are located at the best crossing point.
Good location of the road alignment is the best way to reduce costs - try to avoid
areas that will consume a lot of workdays overcoming natural obstacles.
The alignment finally selected is often a choice between several alternatives. Each of these alternatives needs to be studied in detail, working out how they can be solved, and the amount of work and costs involved. For example, one could avoid an expensive structure by means of a longer route that went around the water course.
In this case, one would have to consider the cost of the structure against the cost of the increased road works.

## Slide 10
Engineers and technicians working on road projects may find the following notes on
design useful:
• Plan the route so as to minimise material movement.
• Select watershed locations and follow contour lines in mountainous terrain as much as possible.
• Plan the route to avoid numerous or large river crossings. Select crossings where
bridge construction will be simple or where ferry crossing will be possible at all
seasons.
• When shallow watercourses cross the route, consider the feasibility of a "submerged bridge" with pipe culverts, fords, or paved causeways.
• Consider proximity of suitable road materials when choosing the route.
• Avoid rocky areas and areas with heavy bush clearing.
• Locate the route so as to allow for future upgrading by realigning (e.g. easing of
curves and gradients) and widening.
• Plan sufficient passing places. The road stretch between the passing places should
be visible from both sides.
• If possible, clear the trees up to a distance back from the road equal to the height of the trees (more when the road runs east-west to facilitate drying after rain.
• Avoid two curves with a short straight in between. It is better to combine them into one long curve.

## Slide 11
• Avoid any horisontal curve at the top of or shortly behind a vertical curve where the driver will not be able to anticipate them.
• Avoid steep gradients. Try to keep longitudal gradients below 10%.
• Allow for adequate drainage. Poor drainage is the most frequent cause of failure of a road; a waterlogged road loses much of its load-bearing strength.
• Make drainage ditches wide and shallow. Wide drains allow water to run at lower speed than do narrow drains, which produces less erosion of the channel.
Also, wide drains are less easily blocked and more easily maintained than narrow drains.
• Be considerate with existing farming activities in the area. Avoid any situations
which may trigger soil erosion.

## Slide 12
The final centre line is first selected by means of a series of straight lines. These lines link together at points of intersection. The intersection points are located with the use of ranging rods, and properly marked by pegs. Once the intersection points are fixed, check with the local landowners to see if there is any objection to the proposed lines.
Pegs are used to mark the alignment and the levels of the road. They are made of wood and can be produced locally. They should have a length of approximately 40cm.
The chainage of the road is marked onto the pegs with a water proof marker.
Before construction works starts, reference pegs are placed outside the road formation.
Ensure that these pegs are hammered deep into the ground so that it will be difficult to remove them.

## Slide 13
Before the actual design work can begin, the engineer has to identify the possible technical problems of each works location. Assessment of the technical problems is an important part of the work of the engineers and technicians.
Special attention should be given to:
• drainage,
• horizontal and vertical alignment,
• soil conditions,
• structures needed, and
• sources of supply of materials and water.
The technical assessment of works to be implemented by labour-based methods
basically follow the same procedures as for machine-based methods. However, the use of labour-based methods should be taken into account so that:
• longitudinal haulage of earthworks is limited, and
• construction in weak soils and rock is avoided where possible.
It is important that the choice of alignment or location takes into account the technology that will be used. The engineer preparing the plans has to assess the problems and work out how to deal with them using the resources available.

## Slide 14
The technical assessment for the work should record the following information:
• design cross-section dimensions,
• existing vegetation cover,
• existing soil type and conditions,
• approximate earthwork quantities involved,
• design gradients,
• structures required,
• drainage measures required,
• gravel or laterite requirements,
• quality and sources of supply of laterite, crushed stone, water, etc.,
• quarry preparation work and hauling distances,
• required work force and availability of labour, and
• type and number of equipment items needed.

## Slide 15
When collecting information regarding the site conditions, it is important that it is
recorded in an organised manner which can easily be referred to at any time during the duration of the road works project. For this purpose, it is helpful to use a standardised form where the details of the envisaged works is recorded.
The "Proposed Road Alignment Sketch", is a form which records the initial assessment of planned works on a road construction project. In this form, detailed information can be recorded for any given section of the road.
Once the initial road alignment has been determined, the Supervisor and Engineer will carry out a survey of the road to estimate the amount and location of construction works.
Information about road curvature, earthworks (cut to fill, embankments, etc.), drainage structures (bridges, culverts, mitre drains, scour checks, etc.) is then plotted in the road alignment sketch at its exact chainage along the road alignment.

## Slide 16
When a final choice of the exact position of the road alignment has been made, the next step is to carry out a full estimate of quantities of work. The expected work quantities form the basis of the cost analysis and determine future inputs of labour, materials, tools and equipment.
Based on the information recorded in the road alignment sketches, it is possible to carry out a first estimate of the construction quantities. This form is more detailed than the Proposed Road Alignment
Sketch, since it records envisaged quantities of work on all future work activities. It
may therefore be necessary to re-visit the road alignment to carry out more detailed assessments of the quantities of work.
Based on these field surveys, the detailed information on volume of works is compiled in the "Estimate of Construction Quantities" form.

## Slide 17
ACTIVITY |  | Unit |  | KM |  |  |  |  |  |  |  |  |  | Total |  | Task rate |  | Workdays | 
 |  |  |  | 0-1 |  | 1-2 |  | 2-3 |  | 3-4 |  | 4-5 |  |  |  |  |  |  | 
SITE PREPARATION |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Clearing | m2 |  | 1700 |  |  |  |  |  |  |  |  |  | 1,700 |  | 75 |  | 23 |  | 
Stump and Rock Removal | No. |  | 6 |  |  |  | 1 |  |  |  | 2 |  | 9 |  | 4 |  | 2 |  | 
Grubbing | m2 |  | 3000 |  |  |  | 3000 |  | 3000 |  |  |  | 9,000 |  | 55 |  | 164 |  | 
Setting Out | m |  | 1000 |  | 1000 |  | 1000 |  | 1000 |  | 1000 |  | 5,000 |  | 50 |  | 100 |  | 
EARTH WORKS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Excavation to Level | m3 |  | 105 |  | 730 |  | 135 |  | 45 |  | 96 |  | 1,111 |  | 1.5 |  | 741 |  | 
Ditching & Sloping | m3 |  | 1075 |  | 165 |  | 748 |  | 725 |  |  |  | 2,713 |  | 1.6 |  | 1,696 |  | 
Forming Camber | m2 |  | 5500 |  | 5500 |  | 5500 |  | 5500 |  | 5500 |  | 27,500 |  | 80 |  | 344 |  | 
Watering and Compaction | m2 |  | 5500 |  | 6130 |  | 5500 |  | 6256 |  | 11800 |  | 35,186 |  | 90 |  | 391 |  | 
Reshaping | m2 |  | 5500 |  | 5500 |  | 5500 |  | 5500 |  | 5500 |  | 27,500 |  | 80 |  | 344 |  | 
EMBANKMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Fill less than 50 cm | m3 |  |  |  | 282 |  |  |  | 360 |  | 3041 |  | 3,683 |  | 1.8 |  | 2,046 |  | 
Fill over 50 cm | m3 |  |  |  |  |  |  |  |  |  |  |  | 0 |  |  |  |  |  | 
GRAVELLING |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Excavation, Load, Haul | m3 |  | 990 |  | 990 |  | 990 |  | 990 |  | 990 |  | 4,950 |  | by contract |  |  |  | 
Spread and Compact | m3 |  | 990 |  | 990 |  | 990 |  | 990 |  | 990 |  | 4,950 |  | 8 |  | 619 |  | 
Average Haul Distance | km |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | TOTAL |  | 6,470 | 

## Slide 18
Construction Targets
The setting of construction and productivity targets is essential for project monitoring.
The comparison between well established targets and actual achievement allows for a realistic judgement of the performance of a work unit or site. Targets must not only be set for outputs in terms of quantities, but also in terms of quality.
The degree of details of targets varies with the level of project organisation:
• at site level targets are established for individual activities,
• at field unit level only the summary or control targets for a number of sites are
required,
• at provincial level targets per field unit would be established and monitored, and
• at headquarters level the national and overall project targets are set and monitored.

## Slide 19
To be able to set targets, the following information must be known:
• the technical standards to be achieved,
• the quality standards to be achieved,
• the quantity and difficulty of the work,
• current task rates and productivity, and
• resources required and available (labour, materials and transport, etc.).
However, there are other factors that influence productivity and operational plans.
Some of these are beyond the control of the management, but must be allowed for:
• climate and rain seasons,
• cultural customs and traditional skills, and
• work incentives.
Once targets have been established, the planner can calculate the cost targets. The work plans may have to be revised in line with availability of funds.
Most projects will have a total plan, to achieve final project objectives, and annual plans to plan the work over a financial year.

## Slide 20
For operational planning only main targets are necessary, such as:
• workdays per km,
• cost per km,
• number of km completed
Time Management Planning
Construction timing is an important part of operational planning. Generally, two
planning phases are used - a long term planning phase (annual work plan) and short term planning phases (monthly or weekly work plans).
Annual Plan
The annual plan is prepared by the Provincial Engineer at DCTPC in consultation with
the management at Ministry level. The list of priorities and the assessment of work
quantities provide the data required for preparing the work time schedule.
Generally, the annual work plan will contain the following:
• name and location of the works,
• target quantity of work for each works location,
• type of work by works location,
• workdays and equipment-days (targets) for each works location,
• starting and finishing month for each works location,
• estimates of cost for each works location, and
• summary totals.

## Slide 21
Construction Sequence
Once the site camp has been established and supplied with materials, tools and
equipment, the road construction works can commence.
Road construction works are divided into a number of operations, each sub-divided into a series of activities. The separate operations on a construction site have to follow each other in a logical sequence. The table below gives a general view of the works sequence on a road construction site:
Operation | Activities
Support | work at site camp, setting out alignment
Site Clearing | detailed setting out, bush clearing, grubbing, tree and boulder removal
Earthwork | excavation and filling, spreading and levelling, drainage and camber formation, embankments
Compaction | watering, compacting and final levelling of earth works
Structures | drifts, culverts and small bridges
Gravelling | excavation and transport of gravel, un-loading, spreading, watering and compaction

## Slide 22
Daily Work Planning
A supervisor must always plan ahead by at least one day. After the
workers have completed their daily work, the supervisor records the
outputs achieved on each of the activities. Based on the production
achieved and the overall plan for the project, a plan for the following day
is prepared. This plan sets the daily production targets for each of the
planned activities.
To prepare these work plans properly, the supervisor needs to know what
has happened on the site before. Without information such as what
resources were needed to produce a given output, why certain targets were
not met, etc., proper planning is impossible. To get the right information on time, a well functioning reporting system is required

## Slide 23
Gang Balancing
Balancing of gang sizes, i.e. ensuring that the labour is used in the most efficient way, and that each of the operations on average proceed at the same pace, is the daily task of the site supervisor. The size of the gang will vary according to the work being undertaken, and depends on:
• the amount of work to be done on each operation,
• the task rates being used,
• the available labourers, and
• the sequence of operations.
Good gang balancing is important because it also determines the length of the
construction site. If the gangs are not well balanced, the result may be that the work site spreads out and becomes to long to supervise in an efficient manner, or that it becomes to concentrated and the workers are working in a small and congested area.
The amount of work will vary along the road line. Therefore there will be a demand
for adjusting the number of workers in each gang.

## Slide 24
Control of Works
The supervisor needs to inspect and approve the work before the workers are released for the day. He/she should be notified by the gangleader, who informs him/her that a particular task has been completed and is ready for inspection.
If the work has been satisfactorily completed, the group or individual may be released for the day.
If the work is not complete, it should be corrected before the group or individual worker is allowed to leave the site.
If the task is not completed before the end of the normal working
day, the supervisor needs to find out the cause of the delay -
whether the cause lies with the workers or with his/her own setting of the task.
If the reason for non-completion is one of the following, the workers should be
released:
• major difficulties were not envisaged when the task was set (i.e. heavy roots, big rocks, etc.),
• incorrect measurement or calculation of the task,

## Slide 25
Site Camp
Before road construction works can commence, a site camp needs to be set up to accommodate the supervisors, materials, tools and equipment. The site camp needs careful planning to provide site staff with a basic comfort, and adequate storage and security for equipment and materials.
Location
The selection of a suitable camp location should be made by the supervisor and the engineer. The following items should be taken into consideration:
􀀹 it should be close to the construction site, preferably in walking distance,
􀀹 it should have access to drinking water,
􀀹 it should be located on high, well-drained land,
􀀹 it should have sufficient space for parking equipment after working hours, and
􀀹 it should be easily accessible to project vehicles bringing equipment and materials.

## Slide 26
The size of the camp depends on the size of the project, what type of works will be
carried out and how far the site is located from headquarters.
In most cases, the site camp can be set up in a local village through which the road will pass. Then, suitable accommodation and stores can be rented from the local villagers. In more remote places, the entire site needs to be established by the project.
Standard requirements for a site camp are:
􀀹 accommodation for the supervisors and equipment operators,
􀀹 a site office,
􀀹 a site store,
􀀹 appropriate cooking facilities,
􀀹 toilet and bathroom facilities, and
􀀹 extra site store for fuel, oil and lubricants.
For a road construction project covering more than 7 to 8 kilometres, the camp will
probably have to be moved once, twice or even several times. These moves have to be planned well in advance so that the necessary transport can be arranged.

## Slide 27
Handtools
Tool requirements depend on various factors such as the size of the project, soil types, terrain and the type of works which are planned. The below table indicates the required hand tools for a project employing a labour force of 100 workers or 200 workers.
Item | 200 workers | 100 workers
Profile Board Ranging Rod Hoe Hoe Handle Shovel Spade Pickaxe Pickaxe Handle Crowbar Bush Knife Axe Bowsaw Grass Slasher Heavy Duty Rake Hand Rammer Wheelbarrow Sledge Hammer Bucket Watering Can Fuel pump 30m Measuring Tape 3m Measuring Tape Line Level Nylon String | 100 100 150 150 75 30 75 75 10 10 15 7 15 40 25 60 3 10 10 1 3 3 3 300 m | 70 70 70 50 50 20 25 25 5 5 5 4 10 30 20 40 3 8 8 1 3 3 3 300 m

## Slide 28
Maintenance
Ensure that the tools on site are in good order, that the tools are sharp and that the
handles are firmly fitted and not damaged. When you find damaged tools on site, report this to the store keeper and have them repaired or replaced immediately. This will increase work efficiency and enable the workers to complete their task work on time.
On large projects, it may be useful to employ a person to maintain and repair handtools.
Alternatively, it is always useful to check with the local villagers if there are any
blacksmiths or carpenters available in the neighbourhood.
Make sure that the camp is equipped with effective sharpening tools and a sufficient
supply of spare parts. The tools required to carry out routine maintenance are cheap
and simple to use.
The cutting edges of axes, hoes, mattocks and grass slashers are normally sharpened
with wet-stones. The edges of other cutting tools are best kept sharp by a selection of
flat, half round and round files. For saws, small triangular shaped files, with a side
about twice the depth of the teeth are appropriate.

## Slide 29
A simple vice should be available at the site store to enable the store keeper to work efficiently.
A vice will enable hand tools to be firmly gripped when maintained or
repaired.
Have a sufficient supply of spare handles on site. A loose or damaged handle is dangerous and should be fixed immediately. Purchase good quality handles made of hard wood which are properly designed according to established standards.
Do not rely on makeshift handles made locally on site.
Wheelbarrows need a lot of maintenance to remain serviceable. Each day, all bolts and nuts should be tightened.
If a bolt is lost, it should be replaced before the wheelbarrow is used again. If the wheelbarrows have pneumatic tires, supply the store keeper with a pump and patching equipment.

## Slide 30
Storage
Tools are issued by the store keeper to the workers every morning and returned in the
afternoon after completion of works. Ensure that the workers are issued the correct
type of tools according to the work activity they will be carrying out. The store keeper
is responsible for keeping full records of the tools and controlling the daily issue of
tools to the workers. The total amount of tools on site needs to be counted regularly
and reported back to headquarters.
The size of the store depends on the amount of tools to be stored. When the road site is very isolated, the store has to be well stocked and therefore tends to be larger in size.
Tools should be stored in a dry and secure place. Stock the items neatly so that they can easily be counted.
Stock different items separately and stock items of different sizes separately.
If necessary, employ a watchman to guard the stores when the storekeeper is off duty.

## Slide 31
Each piece of equipment has an Operators Manual, which specifies when and where lubrication and adjustments are required. As a rule of the thumb, the following activities should be carried out on a daily basis:
Clean and Check
􀀹 lubrication oil level
􀀹 radiator water level
􀀹 hydraulic oil level
􀀹 hydraulic hoses and couplings
􀀹 grease nipples/tracks
􀀹 battery terminals and battery water
􀀹 connections from alternator
􀀹 all the V-belts and their tension
􀀹 tire pressure/tracks
􀀹 transmission oil level
􀀹 brake and clutch fluid level
􀀹 nuts and bolts of buckets and tracks

## Slide 32
Materials
Supply of materials should be made well in advance of its planned consumption. Ensure that sufficient materials are available on site before commencing the works for which the materials are planned. Also, notify the engineer in good time when stores need to be replenished.
When materials are received on site, it is the responsibility of the store keeper to inspect and verify that the stores are in good order and correct quantity. Finally, the materials are recorded in the stores ledger.
Fuel, Oil and Lubricants
Fuel, oil and lubricants should be stored separately, away from the other supplies. These items can be a fire hazard, if not treated properly. Make sure that there are no open fires nearby, such as fire places for cooking, etc.
Fuel is normally stored in drums. Make sure that all consumption of fuel, oil and lubricants are properly recorded and accounted for.

## Slide 33
Culvert Rings
Culvert rings are normally stored at the road site at the planned location of the culvert. They need to be handled with care, in particular when off-loading to avoid that they break. When ordering culvert rings always order a couple of spare rings in case of breakage.
Cement
Cement is very expensive, so it must be handled and stored with care. Avoid breaking the sacks when handling and keep it in a dry and flood secure place. Stack the cement bags off the floor. Always use the oldest cement first.
Pegs
Wooden pegs for the setting out activities are normally produced on site. They should be made well in advance so that the sites have sufficient supply when they are needed. Production of pegs should be organised under the responsibility of the store keeper. If necessary, an additional person can be hired for the collection of wood and cutting of the pegs.

## Slide 34
The Basic Principle of Setting Out
Acommonly used setting out procedure is based on the use of a series of profile boards and a string line level giving control of levels during construction. As a result, the method has become known as the "Profile Board Method".
The basic principle when using profile boards is that when we set them out we are putting up a series of level boards that show us the level 1 metre above the completed construction levels. With practice, it becomes easy to work with these tools and roads can be built properly, economically and at high quality standards.
To ensure that we obtain the correct level in the ditch, we would put up profile boards at positions A and B, 1 metre above the level we want the ditch to be:

## Slide 35
Traveller
We need a third profile board that we can move around. It is known as the travelling profile or traveller. Along the line from A to B, we excavate slots to the level of the ditch. If we place the traveller in a slot and sight from profile board in position A to the profile board in position B, we can see if the traveller lines up with the two fixed profile boards. If the traveller is too low, the slot has been dug too deep. If the traveller sticks up above the sight line, the slot needs top be dug deeper.
To provide good guidance, slots are dug at regular intervals, say at every 4 to 5 metres along the sight line.
When sufficient slots have been dug, the workers can start excavating the ditch by joining up the slots. The traveller can then be used to check that the finished work is to the correct level and that there are no high or low spots.

## Slide 36
0.6 0.6 5.5
This section describes step by step the setting out the road camber of a road
section in rolling and hilly terrain. If the road needs to be elevated on an embankment, refer to the section covering Embankment Construction in Module 5 Construction Procedures.
Normally, the road camber is set out together with the side drains. Once the position and levels of the centre line has been determined, it is possible to construct the camber and side drains.

## Slide 37
When setting out the road camber and side drains, it is important to reduce the amount of excavation to a minimum by following the existing level of the terrain along the road line. The procedure described below is an efficient way of setting out the road levels, achieving a well placed road with good drainage and which does not involve massive excavation and/or fill works.
Step 1: Using the previously set out centre line, set out ranging rods at 10m intervals along the centre line for a section of 50 to 100 metres. At the start of the section, measure out the position of the road shoulders and the outer end of the side drains from the centre line. Repeat this exercise at the other end of the section.
Place a wooden peg next to each of the ranging rods.
Step 2: Once the key positions of the road has been set out at the start and the end of the road section, sight in intermediate ranging rods at every 10m along the road shoulders and side drains.

## Slide 38
Step 4:
Go to the centre line ranging rod at the other end of the road section and repeat the procedure, measuring up 1m from the ground level.
Step 3:
On the centre line of the road, fix the first profile board. This profile may be already in position as the last profile from the previous setting out. If not, measure 1m up from the existing ground level, and mark this level on the ranging rod. Fix a profile board to the ranging rod so that the top edge of the profile board is at the mark made on the rod.

## Slide 39
Step 5: By sighting in the intermediate profiles from one end, fix profile boards on the
intermediate ranging rods along the centre line so that they are all at the same level.

## Slide 40
Step 6: Check the height of each profile board above the ground level. If the height is
approximately 1m, there is no need to adjust them and you can use the level of the profile as it is.
If the height of the profile boards is greater or less than 1m by 10cm, then inspect the line. There may be humps or depressions along the line. The set out line will in most cases smooth out these variations. However, it may be that the set out line is over a hill or a dip in the terrain. In such cases
in the two figures below.
Adjust the profile at position D so that it is 1m above the ground and then lift the profiles at B, C and E to sight in line with the profiles at A to D and D to F. This exercise will reduce the amount of excavation works.

## Slide 41
General Rules
1. It is better to lift profiles than to drop them.
2. Try to keep lifts and drops less than 10cm.
3. Try to match the road levels to the terrain.
4. Use the profiles to get a picture of the vertical road alignment.
.
Before starting on the next step, make sure that the side drains can be emptied. It is important to spend time on this step to get the levels right. All other levels will be set out based on the profiles along the centre line of the road.
Step 7:
Transfer the levels to the ranging rods at the outer end of the side drains. Start with
the beginning of your road section. Using a string and a line level, transfer the level of the profile board at the centre line to the ditches on the both sides of the road. Once the levels are set out with profile boards, mark the levels on pegs next to each ranging rod.
Repeat this procedure for the same two ranging rods at the other end of the road section and for any intermediate profile along the centre line that was lifted or
lowered to reduce excavation works. Then, sight in the intermediate side drain levels.

## Slide 42
You will notice that the height of the drain profile on the low side of the centre line is more than 1m in most cases. This is because we have started from higher grounds, and since the road is level, the lower side drains will be less deep.
Step 8:
Mark the levels for the centre line on pegs placed next to the ranging rods along the centre line. Now use the centre line profile boards to set out intermediate pegs placed at every 5 m along the centre line. This is easily carried out with a 1m traveller. Mark these pegs at the point where the bottom of the traveller touches the peg, when lined up with the profiles. On all the centre line pegs, mark the level of the crest of the camber 0.25m above the 1m level on the pegs.

## Slide 43
Step 9: Place the levels of the shoulders along the road. For this, it is useful to have a traveller 1m high. If we line up the traveller along the line between the two side drain profiles, the bottom of the traveller will show the correct level of the shoulder.
Place pegs every 5m along the edge of the shoulder, and using the traveller, mark these pegs at the point where the bottom of the traveller ends when it lines up with the profiles.
Step 10: Locate and set out the mitre drains. It is important that the mitre drains are set out before the excavation works for the side drains and camber is commenced.
Step 11: Set out with string line the side drains that needs to be excavated. Remember to leave out the mitre drain block-offs.

## Slide 44
CLEARNIG
Heavy bush clearing involves cutting down and removing trees, the clearing of
dense bush and scrub and the digging up and removing root systems to
prevent regrowth.
Boulder Removal
Boulder removal can involve hand carrying small boulders, rolling clear, breaking or digging and burying large boulders.
Topsoil Removal
Topsoil removal is usually only needed where the topsoil is deep (10-15cm), very organic and obviously much lower in strength than the soil below. Unnecessary topsoil removal has very little effect on the strength of the road. Topsoil removal is most likely to be needed in river valleys and flood areas that build up silt.
Most agricultural land and open areas are eroded, with a very thin topsoil layer which can
be mixed in with the earthworks for the road construction.
Topsoil removal is executed using task work on an area basis, the area being
determined by the thickness of the topsoil.

## Slide 45
Earth Work
Basically, road construction earthworks involves digging drains and using the
material to build up the camber, excavating cut to fill to form the road and
building up the road on embankments in flat areas with poor drainage.
The earthworks is then simply to excavate the side drains and use this material to form the camber. Ensure that the volume of the side drains is slightly more than what is needed to form the camber. Usually more material is needed than indicated, either because of low spots in the ground or because of unsuitable soil or because the land is never consistently level.

## Slide 46
Cut to Level
The challenges really begin when the road is built on cross sloping ground. The
steeper the cross slope, the more excavation is needed to build the road. Always
avoid steep cross slopes where possible. Locate the road on ridges where possible -
this will reduce earthworks as well as reduce drainage works.
Road construction in cross sloping terrain have the following features:
• the high side drain will have to be dug deep,
• the low side drain is normally not needed, and
• the road will have to be built on a fill on the low side.
The best way to do this is to split the work into two separate stages.

## Slide 47
Stage 1: Excavate the high side and build up the low side and form the
side slope on the low side.
Stage 2: Excavate the high side drain and form the camber.

## Slide 48
The advantages of this method of working in stages are:
• the excavation approximately balances the amount of fill needed,
• the fill material can be obtained as close as possible to where it is needed - reducing the need for longitudinal haulage,
• by levelling the formation only as far as the edge of the road and then sloping down to the natural ground, reduce the excavation and, in most cases avoid the
need for a side drain on the low side.
The excavation and fill are balanced each side of the centre line, but the width of the excavation has to give sufficient room for the side drain to be dug. This fixes the setting out dimensions for excavation on the high side.
Example:
Assuming a road carriage width of 5.5 m and a side drain width of 1.5 m, the total levelling width on the cut side of the centre line would be:
5.5m / 2 + 1.5m = 4.25m

## Slide 49
Day 3 Day 2 Day 1
When the centre line profiles are set out at 1m above ground level, we can measure
the height of the high side profile to tell us:
✔ how steep the slope is,
✔ the depth of the cut, and
✔ the volume of the levelling works and back-sloping.

## Slide 50
When there is little cross slope (the average height of the high side profile is 90 or
95cm), it is possible to dig the high side drain without levelling first. However, there
are advantages to levelling in these conditions. Setting out the side drain is easier on
a levelled surface and the side drain easier to build to the correct shape. The
supervisor will usually level these minor cross slopes.
The setting out in these cases will be different as there is no advantage in levelling
right through to the centre line. The levelling would then be done from the road
shoulder to the outer side of the side drain (from 2.75m to 4.25m, measured out from
the centre line in the example above).

## Slide 51
Please note that the above levelling practice only applies for new construction. When
rehabilitating an existing road, levelling works should be kept to a minimum, leaving the existing road camber in place and only adding onto it where it has been worn down.
We can calculate the volumes to be excavated for the most common profile heights to be found in practice. These volumes can be given to the supervisor in table form and can be used to work out the workdays needed to carry out the excavation and are used to report the volume of completed works.
The slope of ground is not the same along the length of the road. To set out the work we have to find the average slope over a 20m section.

## Slide 52
Camber and Side Drain Construction
Once the excavation and fill have been completed, the road camber is constructed using soils from the side drains and back slope. Excavated soils from the drains should first be thrown to the centre of the road, from where it is levelled out towards each road shoulder to form the camber.
Side drain excavation is done in two stages. First the ditch is excavated, then the side slopes of the ditch is excavated. Normally, one or two days are allowed between each stage to allow sufficient working space for the workers.
The side drain excavation is set out using string line and pegs, and controlled by using ditch templates.

## Slide 53
For both ditching and sloping, tasks are set as a length of the side drain for each worker. The sloping task is normally set slightly higher than the ditching task, because excavation of soil on the slope face is easier to carry out than excavating the ditch.
The soils excavated from the side drains are used to construct the road camber. To achieve an exact and properly levelled camber, the work is set out using pegs and strings.

## Slide 54
Once the soils for the camber has been levelled, the camber is properly compacted. Make sure that the soils contain optimal moisture content.
After compaction has been completed, it is important to check that the final levels of the road camber is exact and to the prescribed standard and quality. This can either be done by setting out the profile boards again and controlling the level between the profiles with a traveller. A quicker method, however less accurate, is to use string lines to check the level of the completed surface.
If the levels are in-accurate, the irregularities should be removed or filled in. If further filling is required, make sure that this patching is also properly compacted. Finally, repeat once again the checking of the levels to ensure that the earthworks are completed to the correct standards.

## Slide 55
Embankments require large amounts of fill material and are expensive to
construct. They should be avoided when possible by selecting a longer route on higher ground. However, this is sometimes not possible in low, flat, agricultural land, where often no alternative route exists.
Wherever possible, material should be excavated alongside the road and carried to the road by baskets or wheelbarrows. If land is not available for roadside borrow pits, or if the material is not suitable, then earth will have to be brought in from the nearest source by appropriate haulage transport. The type of the borrowed soils should be of good quality. Organic soils, and if possible, sand and silt should be avoided. If sand or silt are the prevalent materials in the area, side slopes should be protected with at least a 15cm layer of clayey soils and vegetation to prevent erosion.
It is important to keep the height of the embankment to the least requirement. This is normally considered to be 0.5m above normal flood levels.
Highest annual flood levels are used to determine the embankment height. This information should be available from local inhabitants and should be marked on pegs along the centre line when choosing the alignment.
Centre line alignment should be carefully selected to avoid low lying areas requiring extra fills and areas where suitable material is not available from the roadside.
The below figure summarises the key dimensions of the cross-section of embankments utilised in the ILO labour-based road works project.

## Slide 56
Earthwork Volume Calculations
Calculation of earthwork quantities is especially important for the planning and control of embankment construction operations. It is necessary to apply a simple and accurate method of estimating embankment quantities at site level.
The standard cross-section dimensions are fixed by national or programme
specifications. In this example, we will assume the dimensions used by the ILO project, i.e. a road width of 5.5m, side slopes of 1:2 and a clearance above highest flood water level of 0.5m.

## Slide 57
H, the height of the embankment is fixed by the height of normal flood levels plus a clearance of 0.5m.
The area of the cross-section can then be calculated as: (5.5 + 2H) x H [m2], which is equivalent to cubic metres per metre road length when we calculate volumes.
Example:
An embankment of 0.80m average height would have a cross-section area of:
(5.5 + 2 x 0.8) x 0.8 = 5.68 m2
or 5.68 m3 per metre length.

## Slide 58
However, for the supervisor this does not give sufficient detail to organise the work on a day to day basis.
The embankment will be built up in compacted layers. The width (W), of each layer depends on the gradient of the side slope and the height of the embankment.
The thickness of the layers will depend on the method and equipment used for compaction. Let us assume compaction by a 1 tonne vibrating roller, which can compact a layer about 15cm thick. So, the embankment will need to built in 15cm layers.
The supervisor needs to estimate the volume of each layer to be able to allocate the right number of labourers for the work each day. For an embankment with a 5.5m carriage width, this is calculated as follows:
The first layer (at the top) 6.1 x 0.15 = 0.91m3 per metre or 18.3m3/20m, the second layer 6.7 x 0.15 = 1.01m3 per metre or 20.1m3/20m,
the third layer 7.3 x 0.15 = 1.10m3 per metre or 21.9m3/20m.

## Slide 59
To calculate the regulating layers, we will need to make some practical assumptions:
• that ground levels are to be rounded to the nearest 10cm, and
• that the ground slope between points can be represented as a straight line.
It is then possible to calculate the volumes of layers of different thickness and shape.

## Slide 60
Drainage
Water is the main contributor to the wear and damage of low-volume rural
roads. The water can be in the form of ground water, surface water (streams
and rivers) or rain. Water can damage the road in two ways:
• by washing away the soil (erosion or scouring), or
• by making the road body less strong to traffic (lowering the road bearing
capacity).
It is therefore important to install an efficient drainage system which allows for the
water to flow of the road and away from it as quickly as possible. This is achieved by
a system consisting of the following components:
• road surface drainage which enables the water to flow off the road surface,
• side drains and mitre drains which collect and lead the water away from the
road,
• catchwater drains which catches surface water before it reaches the road,
• scour checks which prevent erosion in the ditches by slowing down the flow of
the water,
• culverts which lead the water from the side drains under the road to the other
(lower) side,
small bridges and drifts which allows the road to cross small rivers and streams
in a controlled manner throughout the seasons.

## Slide 62
Road Surface Drainage
Road surface drainage is achieved by installing a camber on the road carriage way, thereby enabling the surface water to run off to the side drains. The combination of stagnant water on the road surface and traffic will quickly cause erosion of the road surface. Secondly, if surface water penetrates into the road, it will deteriorate the bearing strength of the road body. To avoid these problems all roads are provided with a camber.
The camber is the slope from either side of the centre line towards the road shoulders. The gradient of this slope varies depending on the type of surface materials. For earth and gravel roads, it is recommended that this slope is in the range of 5 to 10 per cent in order to obtain a sufficient run-off.
Since traffic will eventually erode the road surface, create wheel ruts and causing more erosion in the centre of the road, it is recommended that the road camber of a gravel road is constructed at 7 to 10 percent. This will prolong the life time of the road and allow a longer period of time and use before reshaping of the camber is required.

## Slide 63
Side Drains
The side drains need to have sufficient capacity to collect all rain water from the road carriage way and dispose of it quickly and in a controlled manner to minimise damage.
Sides drains can basically be constructed in three forms: V-shaped, rectangular or as a trapezoid.
Sides drains can basically be constructed in three forms: V-shaped, rectangular or as a trapezoid.
The V-shape is the standard shape for ditches constructed by a motor- grader. It can be easily maintained by heavy equipment, however it carries a low capacity. The rectangular shape requires little space but needs to be lined with rock or concrete to maintain its shape. When using labour-based methods, it is possible to construct a trapezoid shaped side drain. This shape carries a high flow capacity and by carefully selecting the gradients of its side slopes, will resist erosion.

## Slide 64
Erosion Control
The main problems for the side drains are erosion and silting. Erosion is caused by a large quantity of water travelling at high speeds. It is possible to reduce the speed by widening the side drain, but the best way to control erosion is by reducing the amount of water flowing through the drain. This is done by using mitre drains to empty the side drain at regular intervals before the volume of water builds up and causes
erosion.
Another method to control erosion is to place scour checks. These are only used in hilly terrain with steep road gradients where it may not be possible to remove water using mitre drains. Their function is to slow down the water flow by reducing the natural gradient of the drain by allowing the drain to silt up behind the scour check.
Silting is caused by sand and silt settling out of the water. This only occurs with slow flowing, or stationary water. It takes time for the particles to settle, so the further the water has to travel in the drain, the more time there is for the silting to take place.
The solution is to empty the side drains frequently by means of installing mitre drains
at regular intervals.
In some cases, it is wise to construct cut-off or interception drains which prevents surface water from reaching the road. These are particularly useful in the surrounding areas to drift approaches, culverts and bridges. They are also effective in channelling away water from the high side of the road in side sloping terrain.

## Slide 65
Mitre Drains
The location of mitre drains should be determined during the initial stages when setting out the road alignment, thereby ensuring that the road receives a good off road drainage. Make sure that sufficient numbers of mitre drains have been located before side drain excavation starts.
Calculating the correct space between the mitre drains can be quite complicated, in principle the more mitre drains provided, the better. A general rule is to:
• wherever possible, provide a mitre drain for every 100m or less, and
• when the road gradient is very small, provide mitre drains at every 50m along the side drain.

## Slide 66
> Make a strong block off in the side drain, and make it easy for the water to flow along
and out of the mitre drain.
Water will always flow the easiest way. The water will try to continue to flow down the side of the road because it is usually steeper and in a straight line. If you want to divert the water into the mitre drain you must make it easier for it to flow where you want it to go.
The best way to provide a strong block-off is to leave 3 - 8m of natural ground on the drain line not excavated. Forming the block-off with excavated material is not as strong. Block-offs act as useful turning points for trucks and other equipment during the gravelling operation. They are also a natural point to off-load and store gravel for future routine maintenance works.
> The amount of water entering the mitre drain cannot be greater than the amount flowing out. Otherwise, the drain will fill up and over flow, often damaging the block off and causing even greater problems at the next mitre drain. In most cases, the standard mitre drain should be big enough to carry water coming from the standard side drain, except when:
• the side drains carry more water than usual,
• the side drain slope is much greater than the mitre drain slope
In such cases, the mitre drain should be made wider than the side drain so that it can carry more water.

## Slide 67
> The length of the drain depends on the terrain ground levels and the slope of the drain.
Mitre drains should be as short as possible. Long mitre drains are expensive, more
likely to silt up or get blocked off, and in general more difficult to maintain.
A good slope for a mitre drain is 2%. The gradient should not exceed 5%, otherwise there may be erosion in the drain or to the land where the water is discharged. In mountainous terrain, it may be necessary to accept steeper gradients. In such cases, appropriate soil erosion measures should be considered. In flat terrain, a small gradient of 1% or even 0.5% may be necessary to discharge water, or to avoid very long drains. These low gradients should only be used when absolutely necessary. The slope should be continuous with no high or low spots.
> Try to select a line for the mitre drains which will connect with natural run-off channels that take the water well clear of the road. If this is not possible, make sure that the next mitre is set out to catch this water before it enters back into the side drains.
> Finally, it is important that the discharged water does not disturb farming activities in the surrounding areas. By discussing the location where to discharge water from the road with the local farmers, it may be possible to achieve solutions which may assist the farmers rather than destroying the water management of their farm lands.

## Slide 68
Block off 3 to 8 m

## Slide 69
When road gradients are steeper than 4%, the drainage water will gain high speed which may cause erosion of the side drains. Apart from leading the water off in mitre drains, scour checks may reduce the speed of water and prevent the water from eroding the road structure.
Scour checks are usually constructed in natural stone or with wooden or bamboo stakes. By using natural building materials available along the road side, they can easily be maintained after the road has been completed. The distance between scour
checks depend on the road gradient. This relation is shown in the following table
Road Gradient | [%] | Scour Check Interval [m]
4 |  | not required
5 |  | 20
6 |  | 15
7 |  | 10
8 |  | 8
9 |  | 7
10 |  | 6

## Slide 70
After the basic scour check has been constructed, an apron should be built immediately downstream using stones. The apron will help resist the forces of the waterfall created by the scour check. Sods of grass should be placed against the upstream face of the scour check wall to prevent water seeping through it and to encourage silting to commence on the upstream side. The long term goal is to establish complete grass covering over the silted scour checks to stabilize them.

## Slide 71
Cut-off Drains
The purpose of cut-off or interception drains is to prevent water from reaching the road, or to direct water to where it can cross the road safely at constructed water crossings such as culverts, bridges, drifts, etc.
These drains, when properly thought out, properly set out and properly built, can be very useful in reducing damage to the road and reducing maintenance costs.
In most cases, it is cheaper and safer to direct water away from the road, using these drains, rather than providing erosion control measures in the side drains. However, there are certain dangers with cut-off drains that must be considered:
• the water usually carries a lot of silt and if not properly built can silt up quickly,
• as they are off the road they will probably receive less maintenance -
especially when they are difficult to maintain,
• when they fail, water will break through in a concentrated flow causing damage, and
• they may be ploughed up or blocked off by people using the land.

## Slide 72
These dangers can only be avoided if careful planning goes into the drains before
construction and if they are built properly. The following precautions should be taken:
• reduce the danger of silting by making sure there is a continuous down hill gradient and that there is a clear outlet at the end,
• make sure they are easy to maintain and that erosion damage is reduced so
that maintenance needs are small (wide with sloped sides),
• make the drain strong - anticipate the possible weak points of the drain where water could break through and strengthen the drain there,
• locate drains carefully after discussion with local people - where people have to cross the drain, provide easy side slopes so that people will not fill the
drain.

## Slide 73
Siting of Culverts
The siting of culverts should be carried out during the initial setting out of the road alignment. It is important that the culverts are regarded as an integral part of the overall drainage system of the road.
If an existing road is being improved, most culvert sites will be obvious, because the road will have been damaged in some way. In such a situation, look for places where:
• small gullies have formed because water has been flowing across the road,
• sand has deposited on the road because of standing water, or
• drains have been badly damaged because they have been carrying too much water.

## Slide 74
Drifts provide an efficient and economic method of allowing water to cross from one side of a road to the other. In the case of drifts, the water is actually allowed to pass over the surface of the road. As a result, the road surface will need special protection to stand up to the flow of water. This is usually done by making a stone packed or concrete surface where the water will pass. The level of the drift will be lower than the road on each side, to make sure that water does not spill over onto the unprotected road surface.

## Slide 75
Site Location
The most important step is to locate a suitable site for the river crossing. If the drift is
wrongly placed, it may result in both extra work during construction and maintenance
afterwards. The main points to consider are:
• The angle between the centre line of the road and the flow of the water should
be close to 90o.
• The site should be on a straight length of the stream bed.
• Avoid places where there are signs of scouring or silting. Both will cause
future maintenance problems.
• Avoid places where there are steep banks which will involve a lot of
excavation and steep approach slopes.
The site should be on a straight length of the road.

## Slide 76
Drift Approaches
The ideal slope for a drift approach is 5%. When considering building a drift, set out the approaches first to see how much excavation is required.
Two profiles are set out to a 5% slope at each side of the crossing. The length of the
approach can be found by means of a traveller 1m high moved along the line of the
slope profiles until it levels up with the slope profiles when standing on the natural
ground.
The traveller can also be used to measure the depth of the dig along the proposed
approach, and this can be used to estimate the volume of excavation required. It may
indicate the need to look for another site for the drift.

## Slide 77
The above is an example of a drift which in principle consists of a porous dam which retains the gravel/rock from being carried away by the water flow. The top of the gabion dam is between 15 and 20cm higher than the river bed at the downstream end.

## Slide 78
Once the concrete has been placed, keep it damp and let it cure for 7 to 10 days. If the length of the slab is less than 12m there is no need for an expansion joint. On long river crossings, make expansion joints for approximately every 10 to 15 metres
Gravelling is carried out to provide a strong surface layer which is passable in
both dry and wet weather, and which does not deform under the expected traffic loads. Together with the road camber, a good gravel surface will prevent water from entering into the road body and thereby avoiding surface water from deteriorating the bearing strength of the road.
In principle, the following methods can be used to gravel a road:
• use of a mix of labour and equipment, or
• use labour for all activities except hauling over distances longer than 150 metres.

## Slide 79
Transport of gravel can be organised in many ways, depending on the distance from the gravel quarry to the site and the type of equipment available to the project. The following table provides a general picture of the types of transport appropriate for different haulage distances:
Distance Transport
10 – 150 m Wheelbarrows
150 – 2000 m Animal Carts
500 – 8000 m Tractors & Trailers
1000 - Trucks
Gravelling away from the quarry implies that the trucks will pass over the newly completed road sections. This method has the advantage that the vehicles frequently pass over the
newly levelled gravel and thereby provide some compaction to the gravel layer. However, this method also have some disadvantages. It requires that the delivered gravel needs to be levelled before a new truck can dump
its gravel and may therefore delay the un-loading. Finally, a large number of heavy traffic on the road may result is some damages to the newly constructed road.

## Slide 80
Work Procedure
Before carrying out any gravelling works, first check that the earth works have been properly carried out and levelled to the exact and required standards. Set up the profile boards once again, and ensure that all levels are correct and that the camber has not been damaged.
Placing the gravel, involves four activities, namely un-loading, spreading, watering and compaction.